## Objective
Make sure all the positive case
Then try to execute negative case

## Credentials
Admin Panel Link | https://elearning.canvasinteriorstudio.com/admin/panel/login
Email | admin@example.com
Password | 123456789
Site: | https://elearning.canvasinteriorstudio.com/
Ref:

## Course Add(Team1)
Section/Path | Bug / Concern Description | Status | Priority | Tester Name | Developer Name | Screenshot | Comment | check
[UI]QUIA Course> Courses card | Course card image size should be as like as Bohubrihi Course Card Image. | Test Done | High | Akib |  | Screenshot
[UI]>QA Courses> See Course List | Actual Result: In course cards the number of available videos in the courses are not presenting accurately | Test Done | High | Kawser |  | Picture | Fixed
[UI] >QA Courses> See Course List | Need to add "All Course" filter option in the Type section. And by default it should be selected. | Test Done |  | Akib
[UI]>QA Courses> See Course List | Suggetion: In course cards the number students in the courses are not presenting accurately | Test Done |  | Kawser |  | Picture | fixed-kawser
[UI]>QA Courses> See Course List>Any Course | Suggetion: All the titles should be in Left Align | Will Do |  | Musfiq alam |  | Picture | NTD
[UI]>QA Courses> See Course List>Catagory | Suggetion: Course Discount is not count in website course card | Test Done | High | Kawser |  | discount card | fixed-kawser
[UI]>QA Courses | This page should be removed. Checked the SS. | Will Do | High | Akib |  | Screenshot | NTD
QA course> Syllabus , Project & Assignments | Actual Result: If we click on the syllabus section it doesn't show any syllabus content rather than it took us to the footer section.Also project & assignments section have some issue with the link. Expected Result: Link should add properly for Course Details, Syllabus, Project & Assignment. | Test Done | High | Roman Khan |  | Syllabus
[UI]>Courses>Career track courses>java course>রেজাল্ট / এসাইনমেন্ট শোকেস | Actual result - elipsis is displayed between the pictures(Carasole pointer) Expected Result - The ellipsis should:be aligned directly below the pictures positioned centre, should not be overlapped. | Test Done |  | Tanzila Kamal |  | Ellipsis
[UI]>QA Courses> WHAT OUR STUDENT SAID | Student reviews should be course specific. One course's review should not be show to another course's review | Dev Done | High | Akib |  |  | NTD
QA course>Course details>Java course | Suggestion: Instructor and frequently asked question should be separate section. | Test Done |  | Roman Khan |  | FAQ
QA course>Manage Courses>Course Title | Actual Result: Texts in a row does not have a column limit as it goes beyond page boundary Suggetion: The displayed text should have a limit in a row after which it should move to new row | Dev Done | Low | Musfiq alam |  | Main Page View
QA course>Manage Courses>Course Detail Section | Actual Result: Discount price is taking more than 100% Suggetion: Course discount price should always be within 0-100% for avoiding misclick issue | Test Done | High | Musfiq alam |  | Admin Page View
[UI]>QA courses>Career track course>Java course | Actual Result - The right-side section does not scroll, remains static untill the absolute bottom section. Expected Result - The right-side section should scroll smoothly along with the entire screen as the user scrolls down the page | Test Done |  | Tanzila Kamal |  | picture 1 picture 2
[Admin panel]>QA course>manage course> Java course | Suggetions: Multiple Instructors should be selectable at a time. | Future Discussion |  | Kawser |  | Instructor | NTD
QA course>Manage Courses>Module Section>Content Selection Section | Actual Result: Does not present any text input in text & resource or video type content doesn't take any uploads. Expected Result: Content types needs to be addressed properly. | Dev Done | Low | Musfiq alam |  | Main Page View
Admin panel>QA course>manage course> Java course>module section | Actual Result - The changes made in the Position Module don't reflect on the website, even after refreshing Expected Result - Changes made in the Position Module should immediately or after refreshing reflect on the Website UI | Dev Done |  | Tanzila Kamal |  | picture 1 picture 2 | not fixed
Admin Panel > QA course>Manage course>All course>Project & Assignment | Suggetion: It should be project & assignment not project && assignment. | Test Done |  | Roman Khan |  | &&
Admin Panel > QA course>Manage Courses>Module Section>Project & Assignment | Actual Result: When trying to change the image of an already added project, no new image can be added. We can not even add the initial image. | Dev Done | Medium | Musfiq alam |  | Admin Page View
Project && Assignment > Add project | User Interface is not designed properly. | Dev Done |  | Akib
QA Course> Courses card | Suggestion: Both of the courses should remain in the same margin | Test Done | Medium | Roman Khan |  | Course-Card
QA course>Manage Courses>Module Section>Content Selection Section | Actual Result: Does not take any text input in text type content. Expected Result: Content types needs to be addressed properly | Dev Done | Low | Musfiq alam |  | Main Page View
[Admin Panel] QA Course> Manage Course> Click Add Course | Actual Result: able to create a course without a chosen instructor Expected Result: Without a instructor a course should not be created. | Future Discussion |  | Kawser |  | without instructor
[Admin Panel] QA course > Manage Course > Click Add Course | Actual Result: Capable of developing courses without the need for project and assignment additions or course purpose. | Future Discussion |  |  |  | Picture | NTD
Admin panel>QA course>manage course> Java course | Actual Result: In the Admin Panel, it shows: Course Start & Admission Over. In the UI, it shows: Admission Start & Admission Over Expected Result: In the both Admin Panel and UI site, it should shows: Course Start & Admission Over. | Dev Done | High | Tanzila Kamal |  | Screenshot1 , Screenshot2 | not fixed
[User panel]>QA Courses> See Course List | Actual Result: Can't select multiple checkbox in course type of course list | Future Discussion |  | Musfiq alam |  | Picture
[User panel]>QA Courses> See Course List>Any Course | Suggetion: Course Complete Curriculum modul's name should not include "module 1:" | Dev Done |  | Musfiq alam |  | Picture
[User panel]>QA Courses> WHAT OUR STUDENT SAID | Actual Result: Video link apears in a separate duplicate picture. Expected Result: It should apear in the same picture. | Dev Done |  | Kawser |  | Picture
QA course>course details>Any course | Suggestion: Need to fix the site's dynamic rendering logic. | Test Done |  | Kawser |  | Purpose | NTD
[Admin Panel] > Manage Course | Expected Result: Admin can add courses. Actual Result: Admin can't add new courses. | Test Done |  | Roman Khan |  | CourseAdd
| Student feedback design should change, follow bohubrihi for that. | Will Do |  | Akib
Admin > Manage Course | Admission Over date can not set after Course Start admisssion. | Will Do |  | Akib
UI > Course Details | Time left for admission to close' clock is not working properly. It shows more then 3 hours. | Will Do
[Admin] > Manage course> Module | Expected Result: Admin can update course module as many as wants. Actual Results: Admin can't update modules also can't update multiple modules. It only accepts the video url. |  | High | Roman Khan |  | Module_error
UI> My courses>Lesson | Actual : Course lessons counter didn't work properly Expected: Counter should show the actual numbers. |  |  |  |  | Lesson_counter_error

## Blog Add(Team2)
Section/Path | Bug / Concern Description | Status | Priority | Tester Name | Developer Name | Screenshot | Comment
Blog Add>Description(English) | We cannot customize the format of the paragraph when we want to. like Bold,point,Big title, link, paragraph etc. After adding it, it shows as plain text from UI. We must need to customize the paragraph. We add a reference for that: Link | Test Done |  | Akib | mohsin | Picture
Blog>Blog Comments>Display Comment | Actual Result: Comment not displayed after successful completion. Expected Result: Comment Should be displayed after successful completion. | Test Done | High | Pratik | Option 1 | Comment
Blog> Add Blog>View Details | Any blog is added through the admin panel, it does not appear in the "View Details" section on the website. This prevents users from accessing or viewing the newly added blog posts.This issue Should be fixed for user beterment & Understanding. | Test Done | High | Nazim |  | View_Details
Blog>Category>Actions | Actual Result:When delete operation is done of a blog category, the blogs associated with the deleted categories are still shown in the website. Expected Result: Any previous blogs associated with the deleted blog categories shouldn't be displayed on the website | Dev Done | High | Ashraful | mohsin | Actions
Blog>Blog Comments> Long Comments | Actual Result: When a long comment (500+ characters) is submitted in the blog comment section, the blog page becomes inaccessible. The page fails to load revisiting. Expected Result: The blog page should load normally, displaying the submitted comment. Otherwise, there should be a limitation restricting users from submitting comments exceeding 500 char. Validation message: | Test Done | Medium | Pratik | mohsin | Long Comment ¦ Long Comment_2
Blog> Blog Comments> Blank comment | Actual Result: When entering only whitespace characters (space, tabs) in the Name and Comment fields, they are counted as valid characters and allow submission. Expected Result: Only Whitespace should be considered as invalid for all the field(Name, Comment, Email). An error message should be displayed also. | Test Done | Medium | Pratik | mohsin | Blank comment ¦ Blank comment_2 | Issue Fixed
Blog>Category>Actions | Actual Result: In the add block category segment, category name in bangla takes english name also. Expected Result: Category name in bangla should take only bangla name. |  | Low | Ashraful |  | Add Blog Category
Blog> Category>Add-Blog | When We successfully submit a blog, the pop up alert shows "Updated successfully" instead of "Created/Added successfully" | Test Done | High | Farjana Santa | mohsin | On time screenshot chouldn't be taken
Blog>Banner>Upload Service Image | Actual Result: No image delete option Expected Result: It is a more useful feature if the service image has an image delete option so that the blog writer can delete banner image if it is necessary and updated the blog banner. | Future Discussion | Low | Nurullah Sany |  | sample
Blog>Blog Comment> Checkbox | Actual Result: The "Save my name, email, and website in this browser for the next time I comment" checkbox on the comment form does not retain the input data as expected. Even when the checkbox is selected, the entered values are not saved for next visits. Expected Result: The previously entered Name, Email, and Website values should auto-filled in their respective fields when revisiting the page, if the checkbox was selected. | Test Done | Medium | Pratik | mohsin | Checkbox ¦ Checkbox_2 | Issue Fixed
Admin Panel > Blog> Blog Writer> Image | Actural Result: The previously selected image is deleted after any new update. Expected Result: Can't delete previously selected image after updates. | Dev Done | Medium | Mrinmoy | mohsin | Image | Need to discuss
Blog>Category>Add Blog Category | Actual Result:Category name takes only special characters and only numbers as input. Expected Result:Title should be words only. There can be numbers or special characters along with the words | Dev Done |  | Ashraful | mohsin | Screenshot
Admin Panel > Blog> Blog Writer> Missing Directories | Actural Result:"Writer Youtube" is missing "Link" at the end. Expected Result: "Writer Youtube" to "Writer Youtube Link" for consistency. | Test Done | Medium | Mrinmoy | mohsin | Inconsistent Formatting | Issue Fixed
Blog> New Blog> View details | Actural Result: When a new blog is updated on the website, clicking on the blog title or "View Deails" link redirects to the blog details page, but the blog content is not displayed. The page becomes blank which preventing users from accessing the blog details. Expected Result:The blog details page should load and display the blog content, including the title, body text, images, and other elements. | Fixed |  | Pratik |  | View Blog ¦ View_blog_2
Blog>Add Blog>Titles | When attempting to enter a title that has already been submitted, the system does not accept it. This prevents the use of the same title more than once. Expected Behavior: The system should allow duplicate titles unless there is a specific restriction for uniqueness. Actual Behavior: The system rejects any title that has been previously entered. | Test Done |  | Nazim | mohsin | Same Title | Issue Not Fixed
Blog>Add Blog>Blog Post Image | Actual Behavior :The image is removed from both the admin panel and the end-user side after editing. Expected Behavior:The image should remain intact after editing the blog post in the admin panel. | Test Done |  | Nazim |  | Blog post_image | Fixed
Blog>Category>Add Blog Category | Actual Behavior: When a new blog category is created, a confirmation modal comes which says that updated successfully. Expected Behaviour: It should say "created successfully". | Dev Done | Low | Ashraful | mohsin | WrongConfirmationModal
User Frontend Blog Page > Blog List or View Details | Actual Result: The writer name, blog date, views and comments are missing from the UI, leaving incomplete blog details. Expected Result: The admin panel UI page should display the blog writer's name, the published date of the blog post, the number of views and the number of comments. | Dev Done |  | Mrinmoy | mohsin | Blog details | Issue Not Fixed
Admin Panel > Blog > Blog Comment > Misspelled | Actual Result: The column heading for "EMAIL" in the Blog Comments section is misspelled as "EEMAIL." This may confuse users and impact the professional appearance of the admin panel. Expected Result: The column heading should be correctly labeled as "Email." | Test Done |  | Mrinmoy | mohsin | Misspelled | Issue Fixed
Admin Panel > Blog > Blog Comment | Actual Result: The admin panel does not provide an option to delete comments. This prevents administrators from managing inappropriate, spammy or irrelevant comments, which is a crucial feature for maintaining content quality and moderation. Expected Result: The admin panel should provide a delete option for each comment, allowing administrators to remove unwanted or inappropriate content. | Test Done |  | Mrinmoy | mohsin | Missing "Delete Comment" Option | Issue Fixed
Blog > Blog Writting > Tags | Actual Result: In the blog writing section of the admin panel, when a tag is selected from the dropdown menu under the "Tags" field, the selected tag is displayed incorrectly. Expected Result: The selected tag should be displayed clearly with its full name visible and properly styled. | Test Done |  | Pratik | mohsin | Tags | Issue Fixed
Blog > Writer's Details | Actual Result: The blog currently includes a "Writer Profile" section that displays details about writers. This section is no longer required and needs to be removed. Expected Result: The "Writer Profile" section should be removed from the blog page. | Test Done |  | Pratik | mohsin | Writer's Profile | Issue Fixed
Blog> Blog post | In the "Blog Post" section of the blog, the writer's profile picture is currently missing. We want to add the writer's image in the red-marked area. | Test Done |  | Pratik | mohsin | Writer's Image | Issue Fixed
Blog> Blog post> View details | Actual Result: On the blog detail page, the image is currently centered but needs to be positioned on the left side of the content. The writer's information is missing in the "View Details" section; it should include the writer's name, designation, and profile picture. Additionally, there is no option to share the blog post. Expected Result: The blog image should be aligned to the left of the content. Writer's information should be displayed, including their name, designation, and profile picture, aligned appropriately within the page layout and a sharing option (e.g., social media buttons) should be available next to the published date to allow users to share the blog post. | Dev Done |  | Pratik | mohsin | View Details | NTD
Blog> New blog | Actual Result: The blog creation feature currently allows uploading only a single image for each blog post. However, blog posts often require multiple images to enhance content presentation and explain concepts better. Expected Result: The "Write New Blog" functionality should allow users to upload and embed multiple images into the blog content. | Test Done |  | Pratik | mohsin | Add Image | Issue Not Fixed
Blog> Blog posts | Actual Result: The "Tag Cloud" section on the blog posts page contains categories that should be clickable. Clicking on a tag should redirect users to a page displaying all blog posts related to the selected tag. Expected Result: Clicking on a tag in the "Tag Cloud" should redirect the user to a page displaying all blog posts associated with that tag/category. | Test Done |  | Pratik | mohsin | Tags | Issue Fixed
Students Panel
Students> Add Students Button | Add Students Button does not look professional. We should fix it to make it professional | Test Done |  | Nazim |  | Students Button | Issue Fixed
Students> Add Students >Email Field | Email validation issue: The email field accepts input without a valid domain (e.g., missing '.com') | Test Done |  | Nazim | mohsin | Email Field | Issue Not Fixed
Students> Add Students >Image | The "Choose File" section allows uploading any photo without enforcing restrictions (e.g., file type, size, or format). | Test Done |  | Nazim | mohsin | Image | Issue Not Fixed
Students> Add Students > Mobile Number | The mobile number field accepts input of any length without validating for a specific length or format. | Test Done |  | Nazim | mohsin | Mobile Number | Fixed
Students> Add Students >( Gender + University + Password) Feilds | Actual Result : We can Add and update without given Gender, University name as well as Password in Add Student section. Expected Result: We should not add any student information without selecting these kind of credentials | Test Done |  | Nazim | mohsin | University | Fixed
Students> Search Option | Actual Result: The search option works only when using the university name. The search text is not shown in the search box when the search result is displayed. Expected Result: The search option should work using name, email, phone number and university name. The searching text must shown at searching field. | Test Done |  | Nurullah Sany | mohsin | Search SearchResult | Issue Fixed
Students> Add students>Gender | Actual Result: Creating or updating student information if we select gender as other it shows different errors. Expected Result: Should not face any error when updating or creating student information. | Test Done |  | Nurullah Sany | mohsin | Gender_set GenderUpdate
Students> Add students>Filter(Gender, Course) | Actual Result: When students are filtered using gender or Course the input field does not show the filtering gender but the result shows. Expected Result: The result shows with filtered gender in the filter field. | Test Done |  | Nurullah Sany | mohsin | GenderFilter SelectCourse | Issue Fixed
Students> Add Students> phone number validation | Actual Result: Any digit is taken as number, phone numbers are usually 6 to 10 digits and mobile number is 11 digits but here 4,5 digits are also taken. Expected Result::If the phone number is not 6 to 10 digits and the mobile number is not 11 digits then something wrong should be shown instead | Dev Done |  | Farjana Santa | mohsin | phone number.png
Students> Add Students >Name Field | Actual Result: The Name Field display a validation Error : ''The name field must be at least 5 characters''. Expected Result The "Name" field should accept input of any length, including less than 5 characters, as per the specified requirement. | Dev Done | High | Nazim | mohsin | Student Name | Issue Not Fixed
Blog>New Blog | Actual Result: In the blog writing section, there is an option to upload multiple images for a blog post. While the interface allows users to add multiple images, only the first image is displayed on the website after the blog is published. The additional images are not visible on the blog post. Expected Result: All uploaded images should be displayed in the published blog post as intended. |  | High | Pratik |  | Multiple Image | NTD or where and how can show multiple image
Blog> Blog Post> View details | Actual Result: On the Blog View Details page, the featured image is aligned to the left side, but the blog post content does not start from the same alignment. Expected Result: Both the featured image and the blog post content should start from the same left alignment, ensuring visual consistency and improving user experience. |  | Medium | Pratik |  | Alignment

## FrontedUI(Team3)
Section/Path | Bug / Concern Description | Status | Priority | Tester Name | Developer Name | Screenshot | Comment
Common | Use Ponteno Sans text font in the common description. | Dev Done |  | Akib |  |  | NTD
Admin Side>Home Segment >Home Banner>Description | Actual Result: When user enter text containing (600 characters or greater than 211 characters) in the description fields and attempts to submit the form, a 500 Server Error is displayed. Expected Result: If there’s a character limit, the system should notify the user with a validation message instead of showing a server error. | Dev Done | High | Liza | mohsin sikder | Home Banner 2 | NOT Fix [Liza]
Admin Side >Home Segment> Home Banner>Description | Actual Result: When entering text exceeding 1000 characters in the Description field, the system displays an incorrect error message referring to the Subtitle field. Expected Result:-The error message should correctly reference the Description field and state: "The Description field/subtitle field must not be greater than 1000 characters." | Test Done | Low | Liza | mohsin sikder | Home-Banner:3 | Fixed
ADMIN>Home Segment>Home Global Trusted | Only image files can be uploaded, and the image must be in one of the following formats:(.jpg, .jpeg, .png, .webp,.svg, .gif, ) Restrictions for video, text, PDF, Excel, and other file types. | Dev Done | Low | Sepon | mohsin sikder
ADMIN>Home Segment>Awesome Things>Title Field | Actual Result: If we add too many characters to the title field, in frontend the style broken, overlaps with the other "Awesome cards" Also, if we add many character got the error. 404 ¦¦ Server not Found. Expected Result: The title's line should be break down to the next line. | Test Done | High | Toukir | mohsin sikder | Screenshot
Home Segment>Awesome Things> Subtitle/ Desctiption Field | Actual Result: "If we add many characters to the Sub Title / Description, it gives an database error. " Expected Result: There should be a proper Error message & need a validation message for 200 characters. | Test Done | High | Toukir | mohsin sikder | Error screenshot ¦¦ Short video
Home Segment>Home Testimonial | Actual Result: It shows me a "Database Error" when I input 500 characters in description box. Expected Result: There should be a proper error message.[300 charac Max submit] | Dev Done | High | Minhaz | mohsin sikder | Screenshot 3
Homepage>Our Services | Actual Result: If we add more than 6 services in the QA service field ,the homepage only showing last 6 services that we added on the admin panel in the homepage. Expected Result: The homepage will show all the services we added on the admin panel when the user click 'Go Somewhere' button. | Dev Done | High | Tamim |  | Data Given Data Showing
Homepage>Our Services> QA Services > Go Somewhere Button | If we want to see more of services then we have click 'Go Somewhere' button. The button name is inappropriate here. - [Suggestion] Change the button name, Like change the button name into 'More Services/ See All Our Services'. link | Dev Done | High | Tamim |  | Service5 | Test Done-Adil
Homepage>qacourse>OUR PARTNERS | Actual Result: The box size depends on the text. If the text is large, the box may not be properly aligned. Expected result: Should have profer allignment. | Dev Done | Medium | Sepon |  | homepage our partner
| Change the UI of Testimonials & Some Awesome Things section. Please follow the QA Harbor website homepage. | Dev Done |  | Akib
| Change the UI of counter section picture animation & make it small . Please follow the QA Harbor Logo animation in website homepage. | Dev Done |  | Akib
UI>Footer>The menu item email&call | Actual Result: The email and phone number there is a line break, email and phone number are shown in the next line. Expected Result: The email and phone number should be shown in a single line. | Test Done | Low | Toukir |  | Screenshot ¦¦ How should be: reference
About Page>The below section of the testimonial>"Book Consultancy" Button | Actual Result: There is no URL added with the button now. Expected Result: Clicking on the button will redirect to the consultancy page or section. | Test Done | Medium | Toukir |  | Watch
ADMIN>Home Segment>Awesome Things | In the admin dashboard, It always shows I'm active in the admin dashboard no matter what page I'm on | Suggestion | Low | Toukir
Home Segment>Home Testimonial | Sub Title/Description in Bangla allows English but is supposed to take input in Bangla. | Suggestion | Medium | Minhaz |  | Not an issue
Home Segment>Home Testimonial | "Showing the number of results" are appearing together with "Previous & Next" button. | Suggestion | Low | Minhaz |  | Screenshot 2
Admin Side>Home Segment >Awesome Thing>Create Awesome Thing ("Back" Button Too Small and Misaligned on "Create Awesome Thing" Page) | Actual Result: The back button on the "Create Awesome Thing" page is small and positioned too far to the right, making it difficult for users to notice and click. Expected Result: The back button should be appropriately sized and aligned according to the design standards. It should be easily noticeable and clickable, ideally positioned with adequate padding from the screen edges. | Suggestion | Low | Liza |  | Awesome Thing
Homepage>Our Services> Title | Actual Result: The title here showing 'Our Services'. Suggestion: 'QA Services' will be more appropiate for the title of this section. | Dev Done | Low | Tamim |  | Service6 | Need to discuss
Admin Side>Home Segment >Home Testimonial>Create Testimonial ("Back" Button Too Small and Misaligned on "Create Testimonial" Page) | Actual Result: The back button on the "Create Testimonial" page is small and positioned too far to the right, making it difficult for users to notice and click. Expected Result: The back button should be appropriately sized and aligned according to the design standards. It should be easily noticeable and clickable, ideally positioned with adequate padding from the screen edges. | Suggestion | Low | Liza |  | Testimonial
Admin Side>Home Segment >Awesome Thing ( Previous and Next Buttons Misaligned | Actual Result: The Previous and Next buttons are appearing together in the same location. The Previous button should be aligned to the left, and the Next button should be aligned to the right. Expected Result: The Previous button should be displayed on the left side of the page. The Next button should be displayed on the right side of the page. | Suggestion | Low | Liza |  | Awesome Things-2
Homepage> Testimonials > Shared Successful Experience > Testimonial Card | Shared Successful Experience' cards are looking very much average and also not so informative for users. There are no information about clients who has already taken service from that organization. -[Suggestion] Need to change the design of the card and also there must be a section within the card where we can see who are the clients or consumers (Like consumers name, company name, designation etc) that taken our services. Link | Suggestion |  | Tamim |  | Testimonial2
Homepage>Our Services> QA Services > Service Card | Actual Result: The service cards are too thin. And there is too much gap between the cards. . -[Suggestion] Increase width of the card. And reduce the gap between the cards. | Dev Done |  | Tamim |  | Service7
Homepage>Our Services> QA Services > Description | If we type English into Bangla description box, then it's accepting the English letters on Bangla description box - It must be accepts only Bangla letters on Bangla description box. | Not an issue |  | Tamim |  | Service3
Admin Side>Home Segment> Home Banner>Description | The system does not support advanced text formatting such as bold, italic, different font styles, and links. Any changes made to format the text are not reflected in the user interface and display as unformatted plain text. This behavior prevents users from properly formatting text within the description or title fields. -The system should support and display text with advanced formatting. | Not an issue | Low | Liza |  | Home-Banner:4
Admin Side>Home Segment>Home Banner> Title & Description (Title and Description Fields Accept Unsupported Languages) | Although both the title and description fields have language restrictions (specifically for English and Bengali), these fields are accepting titles and descriptions in languages other than the allowed ones. This issue allows users to input text in unsupported languages, which should not be permitted according to the system's language restrictions. -The title and description fields should only accept English and Bengali text. The system should block any input in languages that are not supported and display an appropriate error message or prevent the submission. | Not an issue | Low | Liza |  | Home Banner-5
Home Banner>Title & Description (Title and Description Fields Language Validation) | The system fails to enforce language restrictions for the title and description fields. Both the Bangla fields accept input in English, and the English fields accept input in Bangla. This issue allows users to enter text in unsupported languages, leading to inconsistent data. -The Bangla fields should exclusively accept Bangla text and reject any other languages, including English, while displaying an appropriate error message. Similarly, the English fields should exclusively accept English text and reject any other languages, including Bangla, with an appropriate error message. | Not an issue | Low | Liza
ADMIN>Home Segment>Home Global Trusted | The company name should be unique and not case-sensitive (Only two languages should be supported: Bangla and English) | Not an issue |  | Sepon
ADMIN>Home Segment>Home Global Trusted | The company name should not start with a special character Should not be submitted with Only Numbers & special characters. The company name should only use letters, numbers, and spaces The company name should be less than 50 characters | Not an issue |  | Sepon
ADMIN>Home Segment>Home Global Trusted | When I upload an image, after successfully submitting it, it shows me a shorter (not the actual ratio) [suggestions] | Not an issue | Low | Sepon
Home Page>Sub Menu Items>Dropdown | Change request/Suggestion about sub menu items drop-dowm style | Not an issue |  | Toukir |  | Short Video
Home Segment>Home Testimonial | Title in Bangla supposed to take input in Bangla but it also take in English. | Not an issue |  | Minhaz
Admin Side>Home Segment >Awesome Thing ( Cursor Does Not Change to Hand Icon(Pointer) on Hovering Over Previous and Next Buttons) | Actual Result: When hovering over the Previous and Next buttons, the cursor does not change to a hand icon(pointer), which is expected for clickable elements. Expected Result: The cursor should change to a hand icon (pointer) when hovering over the Previous and Next buttons, indicating they are clickable. | Not an issue |  | Liza
UI>Homepage> Our Service | If we input a long paragraph in the description, then the homepage showing a long card, which making that section of the website unflamboyant. - [Suggestion] The card will only show few lines like 3-4 lines, then add a option 'Read more' for reading the further information. Link | Future Discussion |  | Tamim |  | Service1
ADMIN>Home Segment>Home Global Trusted | There are no image size restrictions, but the image size should be under 5MB (request) | Dev Done | Low | Sepon
Home Segment> Awesome Thing admin page | If the title has many characters, then the page width increases, and even in 100 % screen size, no scroll bar comes, because of which we cannot see any content on the right side, I had to reduce the screen size to see. | Future Discussion | Low | Toukir |  | Short Video
<Responsive> Home Page>Menu Items>For mobile device | On mobile devices, all menu items are not available. | Test Done | Medium | Toukir |  | Screenshot | Need to discuss
The Home Banner section "Get Services"& "Hire Experts" buttons | The Home Banner section "Get Services"& "Hire Experts" buttons have no URL added. | Future Discussion | High | Toukir |  | Screenshot
Home Segment>Home Testimonial | Screen is breaking when I input 255 characters. | Future Discussion | High | Minhaz |  | Screenshot 1
Home Segment>Home Testimonial | Previous & Next buttons are appear together. | Future Discussion | Low | Minhaz
Homepage>Our Services | If we try to see more services on the homepage there are no 'Next' after button on the homepage to swipe into the next card. -[Suggestion] Add a button after 4 Service Card to swipe next card from the homepage, so that the website become more user friendly. Like: Link | Future Discussion |  | Tamim |  | Service4
Admin Side>Home Segment >Home Banner>Upload Service Image (Submission Delay for Images Larger Than 4MB) | Actual Result: When the image size exceeds 4MB, the submission process takes significantly more time compared to smaller images. Expected Result: The submission process should take approximately the same amount of time regardless of the image size. | Future Discussion | Low | Liza |  | Home Banner recording
Home Segment>Home Testimonial | Title/Sub Title is accepted is accepted number & special character. -[Suggestion] It should not accept anything without the alphabet. | Dev Done |  | Minhaz
Home Segment>Home Testimonial | Title/Sub Title in Bangla is accepted is accepted number & special character. -[Suggestion] It should not accept anything without the alphabet. | Dev Done |  | Minhaz
Admin Side>Home Banner>Description | Actual Result: When a user fills in all necessary information in all fields and clicks the submit button, the page unexpectedly turns blank.However, the submitted modifications are successfully saved in the backend, which indicates the issue is with the frontend user feedback or redirection after submission. Expected Result: The user should be redirected to a confirmation page, or a success message should be displayed confirming the modification was successfully saved. | Test Done | High | Liza |  | Home-Banner1 | Fixed
ADMIN>Home Segment>Awesome Things>Title Field | Both title and description fields (Bangla and English) are required fields, but there is no instruction here. If no data is given in any of the fields or an attempt to create a "thing" without any data, is found the error "404 ¦¦ Not Found" . Suggestion: It would be better if added an "*" sign for required fields and if anyone tries to create a "thing" without any information or leaves any fields without data show a notice at the bottom of the fields (This field is required). | Fixed |  | Toukir |  | Error Screenshot ¦¦ Short Video
Home Segment>Awesome Things>Pagination | "If we have below than 10 rows, clicking on the pagination "previous" / "next" button got the error. 404 Server not found. Suggestion: If the rows in a single page are below 10 the pagination "previous" / "next" button should not clickable. Also, the pagination and the table entries information are both in middle alignment. [Suggestion] - It would be better if we adjust the alignment left or right. " | Fixed |  | Toukir |  | Error Screenshot ¦¦ Suggestion Short Video
Admin Side>Home Segment >Home Banner>Description (No success message displayed after form submission.) | Actual Result: After submitting the form, the system processes the submission but does not display any confirmation message ( "Submission is done successfully"). This leaves the user uncertain about whether the submission was completed. Expected Result: A success message ("Submission is done successfully") should appear after form submission to confirm the process was completed. | Test Done | Medium | Liza |  |  | Fixed
Homepage>Our Services> QA Services > Description | If we put space between lines, that isn't showing in the home page. - [Suggestion] It must be shown in the homepage. |  |  | Tamim |  | Service2
Home Page>UI>Globally trusted | Image Height weight should fixed |  |  | Sepon
Homepage> Testimonials > Shared Successful Experience > Testimonial Card | Actual Result: All the testimonial cards are showing on the homepage. Which is making the homepage unattractive and tiresomely long. -[Suggestion] Add a slider button before and after the first and last card to go previous or next slide of that section to read more clients review. Link | Dev Done |  | Tamim |  | Testimonial3 | Test Done-Adil

## Reported By Fahim
Bug Title | Bug Description | Steps to reproduce
Missing Validation and Data Loss When Updating Course Details | When updating a course in the admin panel, the system does not display any error message for mandatory fields after clicking the "Update Course" button. | 1-Navigate to QA Courses in the admin panel. 2-Go to Manage Course. 3-Click on Add Course. 4-Fill in the following fields: Title, Title in Bangla, Description, Description in Bangla 5-Click the Save button. 6-Return to Manage Course and verify that the course is created. 7-Edit the created course. 8-Select Course Type and Category Type. 9-Fill in the Course Details section. 10-Click the Update Course button. 11-Refresh the page. Observed Results: 1- No error message or pop-up is displayed to confirm whether the page was saved or not. 2- After refreshing the page, none of the updated information (Course Type, Category Type, Course Details) is saved. Expected Results: 1- An error message should be displayed indicating any mandatory fields that were not filled after clicking the Update Course button. 2- Successfully entered information should be saved and persist after refreshing the page.
Negative Total Price Created Due to Invalid Discount Input | When creating or updating a course, entering a value greater than 100% in the Discount field of the Course Price section allows the system to calculate and save a negative total price. | 1- Navigate to QA Courses in the admin panel. 2- Go to Manage Course. 3- Click on Add Course. 4- Fill in the following fields: Title, Title in Bangla, Description, Description in Bangla 5- Click the Save button. 6- Verify that additional fields for course creation appear. 7- In the Course Price section, input a value greater than 100% in the Discount field. 8- Click the Update Course button. Observed Results: 1-The course is created with a negative total price due to the invalid discount percentage. Expected Results: 1- The system should validate the Discount field and prevent values greater than 100%. 2- An error message should be displayed if the entered discount exceeds 100%. 3- The course should not be created or updated with a negative total price.
Invalid Admission Dates Cause False Countdown Display | When creating or updating a course, selecting an Admission Start Date that is after the Admission Over Date allows the system to save the course. This results in an incorrect countdown being displayed to the user | 1- Navigate to QA Courses in the admin panel. 2- Go to Manage Course. 3- Click on Add Course. 4- Fill in the following fields: Title, Title in Bangla, Description, Description in Bangla 5-Click the Save button. 6- Verify that additional fields for course creation appear. 7- In the Course Start and Admission Over section, set the Admission Start Date to a date after the Admission Over Date. 8- Click the Update Course button. Observed Results: 1- The course is created successfully with no validation error. 2- A false countdown is displayed to the user, based on the incorrect admission dates. Expected Results: 1- The system should validate the Admission Start Date and Admission Over Date to ensure the start date is before the end date. 2- An error message should be displayed if the admission start date is after the admission over date. 3- The course should not be saved with invalid admission dates.
Filtering Option by Course Type and Category Not Working Properly | The filtering option in the end-user panel for Course Type and Category does not function as expected. Some courses are not displayed when applying specific filters, and the expected values do not appear correctly according to the selected category filter. This impacts the user experience by making it difficult to locate desired courses. | 1- Navigate to QA Courses in the admin panel. 2- Go to Manage Course. 3- Create several courses with different Course Types and Categories. 4- Verify that the courses are successfully created and visible in the admin panel. 5- Open a new window and navigate to the end-user panel. 6- Click on QA Courses > Courses and select a specific type of course. 7- Use the filtering options to filter courses by Course Type and Category. 8- Try different combinations of categories and course types. Observed Results: 1- The filtering option does not work correctly; some courses are not displayed when filters are applied. 2- Not all expected courses appear according to the selected Category filter. Expected Results: 1- The filtering option should display all courses matching the selected Course Type and Category combination. 2- All relevant courses should be visible according to the applied filters.

## Team
Team-1 | Team-2 | Team-3
Md.Kawser Ahamed | Asadullah emon | Rizwana Bintay Mostafa | Md. Arafat Hasnan
Roman Khan | Mrinmoy Saha Mugdha | Soma Rahman | Arifuzzman
Most Airin Akter | Md.Abdullah Al Noman | Minhazul Islam | Afsana Aktar
Tanzila Kamal | Md. Ashraful Morsalin | Md.Salah Uddin Sepon | Ahsanul Karim Fahim
Hasib Rahman | Farjana Santa | Md. Rasel Bin Siddique | Anandita Sutradhar
Musfiq Alam | NURULLAH SANY | Toukir Hossain | Abu Tahir MD Mostakim
Nasrin Akter | Tahsin Ferdous Ara Nayna | Sajjad Hossain | Koushik Halder
Kamruzzaman Mridha Sabbir | Pratik Saha Roy | Tamim Billah
Rifat Khan | Md Najim Hossain
Arifuzzman 01962415529 | Md. Arafat Hasnan ( +8801780329372) | Adil Ahmed Khan
Tabassum Ferdous | Md.Fahim Faisal | Niharika Sarker Nitu | Md.Aminul Islam
Ashraf Ahmed Sizan | Md Akdas Ali | Amanullah Arefin Anim
FM Tahoshin Alam | Nazrul Islam Rana
Anika Maisha Tasnim |  |  | Afsana Aktar
Ahsanul Karim Fahim
Anandita Sutradhar
Abu Tahir MD Mostakim
Koushik Halder
Md Istiaque Ahmed
Md Rafi Monjur Khan
Parvas Hossain Piash